Client Agent Unification
Current status of Unified Client Agent work:
Previous stated goals to be complete by mid-December:
“Reboot” (Crossplatform)
PXE/Ghost VLAN switch diagnostic (Crossplatform)
Domain join/unjoin (Windows)
Platform identification (Crossplatform)
Service/Daemon code (Crossplatform)

---
Previous stated goals to be complete by mid-December:
“Reboot” (Crossplatform) ✓
PXE/Ghost VLAN switch diagnostic (Crossplatform) ✓
Domain join/unjoin (Windows) ✓
Platform identification (Crossplatform) ✓

---
Currently working on the service/daemon unification.
Daemon (Linux) segment tested and working.
Service (Windows) segment work in progress.
Current WIP is single codebase which runs on both platforms.

---
Once Service/Daemon work is complete, we will begin pulling in the previous
POC code for reboot, domain join/unjoin, etc into unified agent codebase.
Expect to start this week
Once this is finished, we will have a working unified agent, with the following
caveats:
Agent will not have associated installer/updater (yet).
This was outside of the scope of the current work, but we will tackle it next.
Question as to whether we re-use current installers and update tools, or
come up with a single, unified method.
NMSA, Asset update work will need to be added. Some work on this has
already begun, but it was not part of stated scope.
Other items TBD.

---
When can others start testing?
Once we have the POC code pulled into the unified agent proper after the
service code is complete and we have some semblance of an installation
method (does not have to perfect yet) it will be ready for third-party
testing. (With the caveat that more work still needs to be done to match
feature-parity with current agents.)
Expect to be at this stage by mid-January.